## Sheet1
Agile Project Planning - Create a one-page project plan for a new software feature using Agile planning techniques. Include backlog items with estimated story points and a prioritized list of user stories.
Agile project planning is an iterative approach to managing projects, particularly software development projects. Unlike traditional, linear planning methods, Agile focuses on flexibility and continuous adaptation.
PRODUCT BACKLOG ID | PRODUCT BACKLOG FOR E-COMMERCE APPLICATION | USER STORY ID | USER STORIES | SCRUM TEAM ASSIGNED | USER STORY STEP DEFINITION 1 | USER STORY STEP DEFINITION 2 | ASSIGNED TO | ESTIMATED TIME | ACTUAL TIME | STATUS | REMARK
1 | high | user001 | Login Management | team1 | Create account | Verify email & password | Abdulbasid | 3 days | 3 days | In progress | NA
2 | medium | user002 | Add to cart | team2 | Initiate transfer | Confirm cart | Raushan Kumar | 2 days | 2 days | not started | NA
3 | high | user003 | Incorrect product detail | team3 | Add biller | Check the details | Pooja | 1 day | 1 day | not started | NA
4 | medium | user004 | User Registration | team4 | Fill registration form | Verify email | Sangita | 3 days | 4 days | In progress | NA
5 | high | user005 | Loan Management | team5 | Apply for loan | Upload documents | Paradnya | 5 days | 4 days | not started | NA
6 | medium | user006 | Product suggestion | team6 | Select investment | Check suggestions | Sahil | 4 days | 3 days | completed | NA
7 | low | user007 | Notifications | team7 | Set notification preferences | Receive notifications | Shavej | 2 days | 2 days | not started | NA
8 | medium | user008 | Customer Support | team8 | Submit query | Get response | Abdulbasid | 2 days | 2 days | pending | NA
9 | high | user009 | Admin Dashboard | team9 | View analytics | Manage users | Pooja | 6 days | 6 days | not started | NA